## Bug Summary
AEES
| Issue Encountered | Urgent | Date Reported | Target Date | Target MD | Actual MD | Status | Date Resolved | Release Status | Remarks | Fixed Confirmed | Date
1 | Loan Disclosure Information |  | 2020-06-05 | 2020-06-16 | 1 MD | 0.5 MD | Done | 2020-06-16 | Released (6/16/2020) |  | OK | 2020-06-19
2 | MBF does not auto compute for new member |  | 2020-06-05 | 2020-06-11 | 0.5 MD | 4 MD | Done | 2020-06-11 | Released (6/16/2020) |  | OK | 2020-06-19
3 | Cannot generate excel in Savings and Interest |  | 2020-06-05 | 2020-06-09 | 1 MD | 0.6 MD | Done | 2020-06-09 | Released (6/16/2020) |  | OK | 2020-06-17
4 | Add Payment is not visible in Ammortization Schedule |  | 2020-06-05 | 2020-06-15 | 2 MD | 0.5 MD | Done | 2020-06-16 | Released (6/16/2020) |  | OK | 2020-06-19
5 | Cannot generate excel in Loan Disbursement |  | 2020-06-11 | 2020-06-16 | 0.5 MD | 0.4 MD | Done | 2020-06-11 | Released (6/16/2020) |  | OK | 2020-06-17
6 | MBF does not auto compute for member with Share Capital |  | 2020-06-17 | 2020-06-18 | 3 MD | 1 MD | Closed | - | - | This is not a bug | OK | 2020-06-19
7 | Allotment does not appear in Loan Disclosure |  | 2020-06-17 | 2020-06-17 | 1 MD | 1 MD | Done | 2020-06-17 | Released (6/19/2020) |  | OK | 2020-06-22
8 | Loanable Amount doesn't auto compute after editing and saving |  | 2020-06-19 | 2020-06-22 | 2 MD | 2 MD | Done | 2020-06-22 | Released (6/22/2020) |  | OK | 2020-06-22
9 | Allotment is not visible in loan disclosure when the loan state is draft |  | 2020-06-24 | 2020-06-24 | 1 MD | 0.6 MD | Done | 2020-06-24 | Released (6/29/2020) |  | OK | 2020-07-01
10 | Loanable amount doesnt auto compute after consolidating loans |  | 2020-06-26 | 2020-06-29 | 3 MD | 1 MD | Done | 2020-06-29 | Released (6/29/2020) |  | OK | 2020-07-01
11 | When editing outstanding loan in loan register MBF amount doesnt change |  | 2020-06-26 | 2020-07-06 | 2 MD | 1 MD | Done | 2020-07-06 | Released (7/6/2020) | Please use Recreate deduction from configuration button. | OK | 2020-07-07
11.1 | connected to concern 11 MBF Account does not credited after closing posting |  | 2020-06-30 | 2020-07-02 | 1 MD | 3 MD | Done | 2020-07-04 | Released (7/6/2020) |  | OK | 2020-07-07
11.2 | connected to concern 11 CBU Account does not credited after closing posting |  | 2020-06-30 | 2020-07-01 | 0.5 MD | 0.5 MD | Done | 2020-07-01 | Released (7/6/2020) |  | OK | 2020-07-07
11.3 | connected to concern 11 Approve Loans cannot generate in loan disbursement |  | 2020-06-30 | 2020-07-01 | 0.5 MD | 0.5 MD | Done | 2020-07-02 | Released (7/6/2020) |  | OK | 2020-07-07
12 | [Urgent] Uploading of Allotment, CBU and Savings Account via Excel |  | 2020-07-10 | 2020-07-14 | 2 MD | 2 MD | Done | 2020-07-14 | Released (7/6/2020) | Allotment Client Pending | OK but client has inquiry | 2020-07-20
13 | Uploading Master Data using python |  | 2020-07-10 | 2020-07-15 | 1 MD | 2.3 MD | Done | 2020-07-19 | Released (7/19/2020) |  | OK | 2020-07-19
14 | Allotment Savings Transaction Code for Loan Allotment |  | 2020-10-13 | 2020-10-13 | 1 MD | 1 MD | Done | 2020-10-13 | Released (7/13/2020) |  | OK | 2020-07-15

## Inquiries
AEES
| For Inquiry | Date Reported | Target Date | TARGET MD | ACTUAL MD | Status | Date Resolved | Remarks/Answers | Inquiry Confirmed | Date
1 | For Inquiry on Template for Migration where to put the existing MBF Account? | 2020-06-30 |  | 1 MD | 1.6 MD | Done | 6/31/2020 |  | OK 7/8/20 | 2020-07-08
2 | For Inquiry on additional VPN access for hands on testing on July 4, 2020 | 2020-06-30 |  | 1MD | 1 MD | Done | 2020-07-03 |  | OK 7/8/20 | 7/8/20
3 | Confirmation for uploaded allotment - for checking if possible to disable confirmation or possible if we have bulk approve | 2020-07-20 |  | 1MD | 1 MD | Done | 2020-07-20 |  | OK
4 | If possible to upload Savings CBU and Payment on 1 import | 2020-07-20 |  | 1MD | 1 MD | Done | 2020-07-21 |  | OK
5 | Inquiry sent in email regarding Migration of Savings and CBU Account | 2020-07-21 |  | 1MD | 0.6 MD | Done | 2020-07-22 |  | OK
6 | Inquiry sent in email regarding paid and on going Loan migration | 2020-07-22 |  | 1 MD | 1.4 MD | Done | 2020-07-23 |  | OK
7 | Migration Template Questions | 2020-07-23 |  | 0.5 MD | 1 MD | Done | 2020-07-24 |  | OK
8 | Payment Bulk Approval for loan payment | 2020-07-24 |  | 0.5 MD | 0.5 MD | Done |  |  | OK
9 | Check for the computation of principal balance | 2020-08-11 |  | 0.1 MD | 0.1 MD | Done | 2020-08-24 |  | OK
10 | Python Migration training | 2020-08-12 |  | 0.2 MD | 0.2 MD | Done | 2020-08-25 | Meeting on 08/25 | OK
11 | Python Migration encountered issues (Members.py) | 2020-08-24 |  | 0.1MD | 0.1MD | Done | 2020-08-27 | migration setup | OK
12 | HLD design for Bulk approval | 2020-08-24 |  | 0.1MD | 0.1MD | Done | 2020-08-28 |  | OK
13 | Inquiry for CBU of member types | 2020-08-24 |  | 0.1MD | 0.1MD | Done | 2020-08-28 |  | OK
14 | Migration Inquiries | 2020-08-26 |  |  |  | Ongoing
15 | CBU migration for dep[psit and withdrawal | 2020-10-01 |  | 0.1MD | 0.1MD | Done | 2020-10-01 |  | OK
16 | Error in CBU deduction setup in Loan Register. The GL account is can not be edited | 2020-10-09 | 2020-10-13 | 0.1 MD | 0.1MD | Done | 2020-10-12 | GL Account is the Chart of account for the deduction transaction movement. See WEBCOOP Standard flow. deduction is set on CBU from Chart of accounts | OK